## Sprint 2
Names | Tasks | Story Point | Branch/file Link on GitHub | Comments
Ahmed | Implement wall Ant | 3 | Add_WallAnt_And_Tests | Merged to master
| Implement wall Ant tests | 2 | Add_WallAnt_And_Tests | Merged to master
| Implement Fire Ant | 3 |  | Done with wallant branch. Separate branch not created
| Implement Fire Ant tests | 2 |  | Done with wallant branch. Separate branch not created
| Write user stories for the project | 2 | User Stories of the AntsVsBees system | Uploaded to master
| Blackbox testing | 3 | Class_FireAnt_test.docx | Uploaded to master
Anas | Implement Slowthrower ant | 3 | slowThrowerAnt_and_classes | Merged to master
| Implement long thrower ant | 2 | LongThrowerAnt | Pull request open
| Implement Short thrower ant | 2 | ShortThrowerAnt | Pull request open
| Implement Slowthrower ant tests | 2 | ThrowerAnt_Test
| Implement long thrower ant tests | 2 | LongThrowerAnt_Test
| Implement Short thrower ant tests | 2 | ShortThrowerAnt_Test
| Implement Queen ant tests | 3
| Implement Queen ant functionality | 5 | QueenAnt | Pull request open
Ali | Implement Ninja ant | 3 | add-ninja-ant | Merged to master
| Implement Ninja ant tests | 2 | add-ninja-ant | Merged to master
| Implement testing of bee, ant colony and antgame | 3 | test-beeclass, test-AntColony-class | Merged to master
| Implement buttons for Pause Game, Play/Resume game, Reset Game. | 2 | add-play/pause-functionality | Merged to master
| Implement different levels to the game | 2 | add_levels_to_game
| Implement bodyguard ant | 3 | add-bodyguard-ant | Merged to master
| Implement bodyguard ant Tests | 2 | add-bodyguard-ant | Merged to master
| Implement scuba thrower ant | 2 | add-scuba-ant | Merged to master
| Implement scuba thrower ant tests | 2 | scuba_ant_tests | Merged to master
| Implement water functionality/moat frequency to the game | 1 | add-scuba-ant | Merged to master
Backlog
Ahmed | Update uml diagram with AntGame and AntColony classes | 3 | Classdiagram1.png

## Sprint 3
Names | Tasks | Story Point | Branch/file Link on GitHub | Comments
Create user accounts. Allow saving the level of a game for each user account
Include a help/guide menu that shows the description of each ant and bee
Include the following additional bees: (a) Zombie Bee : can attack 3 ants together (b) Ghost Bee: passes through nearly all ants without any damage. Only Ninja ant and Queen ant can attack/damage a Ghost Bee.